## Sheet1
Topic | Deadline | Owner
Discussion and Finalization of project ideas | 2022-09-11 | Entire Team
Discussion on scope of the project | 2022-09-11 | Entire Team
Preparation of project proposal | 2022-09-18 | Satishwar Kedas
Brainstorming on process of data scraping | 2022-10-02 | Entire Team
Identifying Xpaths for data scraping | 2022-10-09 | Yash Patel, Ashutosh Maharana
Python code for scraping data from main page | 2022-10-16 | Satishwar Kedas
Python code for scraping data from campaign page | 2022-10-16 | Yash Patel
scraping data | 2022-10-23 | Satishwar Kedas
Python code for cleaning the data | 2022-10-30 | Tharun ponnaganti
Data Transformation | 2022-11-02 | Ashutosh Maharana
Report preperation for deliverable 1 | 2022-11-06 | Entire Team
Data visualizations and Insights | 2022-11-20 | Entire Team
Report preperation for deliverable 2 | 2022-11-25 | Entire Team